## Sheet1
Time Breakdown

Summary
Task	Optimistic	Pessimistic	Avg
Users	28.0	37.0	32.5
Products	25.0	34.0	29.5
Orders	29.0	41.0	35.0
Layout	18.0	22.0	20.0
Design	52.0	78.0	65.0
Auth	27.0	33.0	30.0
Admin	9.0	12.0	10.5
Payments	35.0	53.0	44.0
Meta/Hosting	31.0	43.0	37.0

Totals	254.0	353.0	303.5

Users
Task	Optimistic	Pessimistic	Avg
Model	10	14	12
Create/Mod	6	8	7
List	5	6	5.5
Enable	2	3	2.5
Emails	5	6	5.5

Totals	28	37	32.5

Products
Task	Optimistic	Pessimistic	Avg
Model	7	10	8.5
Create/Mod	7	10	8.5
List	5	6	5.5
View	6	8	7

Totals	25	34	29.5

Orders
Task	Optimistic	Pessimistic	Avg
Model	8	10	9
Create	5	8	6.5
View	5	6	5.5
List	5	7	6
Print	9	14	11.5
Emails	5	6	5.5

Totals	29	41	35

Layout
Task	Optimistic	Pessimistic	Avg
Mockups	6	6	6
Templates	12	16	14

Totals	18	22	20

Design (low accuracy)
Task	Optimistic	Pessimistic	Avg
Colours	14	21	17.5
Graphics	28	42	35
Fonts	5	6	5.5
Borders	5	9	7

Totals	52	78	65

Authorization/Authentication
Task	Optimistic	Pessimistic	Avg
Session Model	6	7	6.5
Security Scheme	10	12	11
HTTPS	6	8	7
Login/Logout	5	6	5.5

Totals	27	33	30

Administration
Task	Optimistic	Pessimistic	Avg
Roles	4	5	4.5
Views	5	7	6

Totals	9	12	10.5

Payments (low accuracy)
Task	Optimistic	Pessimistic	Avg

Gateway Interface	14	21	17.5
Forwarding	7	12	9.5
Order Creation	4	5	4.5
Shopping Cart	10	15	12.5

Totals	35	53	44

Meta/Hosting
Task	Optimistic	Pessimistic	Avg
Get Server	2	3	2.5
Domain Name	2	3	2.5
Email	10	12	11
Server Software	10	11	10.5
Merchant Acct	7	14	10.5

Totals	31	43	37